## WBS with Gantt Chart
WORK BREAKDOWN STRUCTURE WITH GANTT CHART TEMPLATE
PROJECT TITLE
PROJECT MANAGER
COMPANY NAME
DATE | [6 empty] | INITIATION |  |  |  |  | PHASE ONE | [9 empty] | PHASE TWO | [9 empty] | CLOSURE
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | % of TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6
[6 empty] | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception & Initiation
1.1 | Project Charter | Leon W | 2022-03-12 | 2022-03-15 | 3 | 100%
1.1.1 | Project Charter Revisions | Kylie R | 2022-03-15 | 2022-03-16 | 1 | 100%
1.2 | Research | Pete S | 2022-03-15 | 2022-03-21 | 6 | 90%
1.3 | Projections | Steve L | 2022-03-16 | 2022-03-22 | 6 | 40%
1.4 | Stakeholders | Allen W | 2022-03-17 | 2022-03-22 | 5 | 70%
1.5 | Guidelines | Malik M | 2022-03-18 | 2022-03-22 | 4 | 60%
1.6 | Project Initiation | Malik M | 2022-03-23 | 2022-03-23 | 0 | 50%
2 | Project Definition & Planning
2.1 | Scope & Goal Setting | Steve L | 2022-03-24 | 2022-03-28 | 4 | 5%
2.2 | Budget | Allen W | 2022-03-29 | 2022-04-02 | 4 | 30%
2.3 | Communication Plan | Malik M |  |  | 0 | 0%
2.4 | Risk Management | Malik M |  |  | 0 | 0%
3 | Project Launch & Execution
3.1 | Status & Tracking | Pete S |  |  | 0 | 0%
3.2 | KPIs | Leon W |  |  | 0 | 0%
3.2.1 | Monitoring | Kylie R |  |  | 0 | 0%
3.2.2 | Forecasts | Kylie R |  |  | 0 | 0%
3.3 | Project Updates | Pete S |  |  | 0 | 0%
3.3.1 | Chart Updates | Malik M |  |  | 0 | 0%
4 | Project Performance / Monitoring
4.1 | Project Objectives | Steve L |  |  | 0 | 0%
4.2 | Quality Deliverables | Allen W |  |  | 0 | 0%
4.3 | Effort & Cost Tracking | Malik M |  |  | 0 | 0%
4.4 | Project Performance | Malik M |  |  | 0 | 0%
Formulas:
DURATION = DAYS([DUE DATE],[START DATE])

## WBS with Gantt Chart - BLANK
WORK BREAKDOWN STRUCTURE WITH GANTT CHART TEMPLATE
PROJECT TITLE | TODO-List
PROJECT MANAGER | Florian Foerster, Koby Stewart
COMPANY NAME | Team TODOList
DATE | 2025-09-04 | [5 empty] | INITIATION |  |  |  |  | PHASE ONE | [9 empty] | PHASE TWO | [9 empty] | CLOSURE
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | % of TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6
[6 empty] | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception & Initiation
1.1 | Stakeholders | Koby S | 2025-09-03 | 2025-09-03 |  | 100%
1.2 | Project Charter | Koby S | 2025-09-03 | 2025-09-03 |  | 100%
1.2.1 | Project Charter Revisions | Florian F | 2025-09-03 | 2025-09-03 |  | 100%
1.3 | Plan Project Timeline & Create Gantt-Chart | Florian F | 2025-09-03 | 2025-09-04 |  | 100%
1.4 | Define Milestones & work packages | Florian F | 2025-09-03 | 2025-09-04 |  | 100%
1.5 | Research (Technologies) |  |  |  |  | 0%
1,6 | Project Initiation |  |  |  |  | 0%
2 | Planning & Prototyping (Sprint 1)
2,1 | Sprint Planning & Task Assignment (Sprint 1) |  |  |  |  | 0%
2,1,1 | Requirements Analysis & Backlog Creation |  |  |  |  | 0%
2,2 | KPI Defintion |  |  |  |  | 0%
2,3 | Architecture & Technology Evalutation (PHP/cPanel) |  |  |  |  | 0%
2,4 | UI/UX Prototyping |  |  |  |  | 0%
2,5 | Backend Proof of Concept |  |  |  |  | 0%
2,6 | Effort Estimation & Budgeting |  |  |  |  | 0%
2,7 | Communication Plan |  |  |  |  | 0%
2,8 | Risk Analysis & Mitigation |  |  |  |  | 0%
2,9 | Review & Retrospective (Sprint 1) |  |  |  |  | 0%
3 | Implementation (Sprint 2)
3,1 | Sprint Planning & Task Assignment (Sprint 2) |  |  |  |  | 0%
3,1,1 | Create Github Repository |  |  |  |  | 0%
3,1,2 | Setup branching strategy |  |  |  |  | 0%
3,2 | Backend Implementation (PHP/cPanel) |  |  |  |  | 0%
3,3 | Frontend Implementation (Web App) |  |  |  |  | 0%
3,4 | Status Badges & Kanban Logic |  |  |  |  | 0%
3,5 | Frontend & Backend Integration |  |  |  |  | 0%
3,6 | Testing & Bug Fixing |  |  |  |  | 0%
3,7 | Monitoring & KPIs |  |  |  |  | 0%
3,8 | Progress & Cost Tracking |  |  |  |  | 0%
3,9 | Review & Retrospective (Sprint 2) |  |  |  |  | 0%
4 | Closure
4,1 | Acceptance & Handover |  |  |  |  | 0%
4,2 | Project Documentation |  |  |  |  | 0%
4,3 | Final Presentation |  |  |  |  | 0%
4,4 | Lessons Learned |  |  |  |  | 0%
4,5 | Final Report & Archiving |  |  |  |  | 0%
4,6 | Review / Project Closure Meeting |  |  |  |  | 0%

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.